## Project Plan
| Project Plan for Hiring | [6 empty] | Wish List
Section | item # | item | Description | Responsible | Due date | time spent | Decision/Comments | Additional Suggestions
Prep for hiring | 1.1 | Job Description | Define the position |  |  | 40 mins
| 1.2 | Job Board | Determine what sites the job should be published on |  |  | 15 mins
| 1.3 | Job Advertisement | Write the job ad (includes about company, job description, due date, call to action: email resume) |  |  | 60 mins
| 1.4 | Compensation | Settle on compensation plan |  |  | 10 mins
| 1.5 | Test administration | Determine what tests should be administered to candidates (ESQ, PAF-A). Determine cutoff scores. |  |  | 5 mins
| 1.6 | Interview Questions | Develop interview questions for phone & in-person interviews
| 1.7 | Review test communications | Review & finalize communication regarding tests taken (links to assessments, rejection emails) |  |  | 20 mins
Post job | 2.1 | Post Job | Job is posted on job board with above details
Candidate handling | 3.1 | Receive resumes | Resumes of top candidates emailed to reviewing committee
| 3.2 | Send tests | Candidates who submit resumes are provided with links to take tests. Send instruction page & testing information, include deadline to complete
| 3.2.1 | Reminders | Send reminder to those that haven't completed by due date
| 3.3 | Review resumes & test scores | Review resumes along with test scores to create short list
| 3.4 | Send acceptance/rejection letters | Emails sent to candidates
Phone Interviews | 4.1 | Call/email short list | Describe position, describe selection process, schedule interviews
| 4.2 | Refine interview questions | Refine interview questions based on scoring criteria |  |  | 2 hrs
| 4.3 | Conduct phone interview
| 4.4 | Identify short list
In-person Interviews | 5.1 | Call/email short list | Schedule in-person interview
| 5.2 | Refine interview questions | Refine interview questions based on phone interview, consider scenario-based interview questions. Consider scoring criteria for interview questions
| 5.3 | Conduct in-person interviews
Hiring decision | 6.1 | Background check
| 6.2 | Reference check | Specific questions for references
| 6.3 | Extend offer
| 6.4 | Finalize employment contract
Pre-start date preparation | 7.1 | Office space
| 7.2 | Training plan | Compile list and materials that will need to be reviewed by hire
Start date | 8.1 | Start date | Potential start date for hire
Training | 9.1 | Basic customer service training (phone, emails)
| 9.2 | Software
| 9.3 | Products
9.4

## Timeline
Suggested timeline | Time needed? | Date suggested
Post job | 1 month | 2015-10-01
Phone interviews | 2 weeks | 2015-11-02
In-person interviews | 2 weeks | 2015-11-16
Hire /start date |  | 2015-12-01